## Sheet1
Sl. No. | Roles | Test Case | Test Execution Steps | Expected Result | Test Result P - Pass F - Failed U - Untested | Date Tested | Tester | Comment
General
1 | All | Loading Ivanti Site | 1. Open Internet Explorer. 2. Enter https://waynecounty-uat.saasit.com/ in the address bar and hit 'Go'. | Ivanti staging site launches | P
2 | All | Log into site with windows credentials | On Ivanti Site: https://waynecounty-uat.saasit.com enter windows username and password | Successful login to Ivanti SM with Service Desk Analyst role | P
Incident
3 | Service Desk | Opening Incident module | After accessing Ivanti SM site click on Incident module. Next, click New Incident | New blank Incident form should appear | P
4 | Service Desk | Verify VIP customer automatically changes priority to level 2 | Enter in Nevena Malbasic in the customer field. | Customer should be flagged as a VIP and the priority change to level 2- High | P
5 | Service Desk | Enter in customer name and verify profile setup | Clear customer field, then type in your name, select name and verify customer profile when it appears. | Customer profile should include name, email address, phone number, and customer location (address) | P
6 | Service Desk | Verify Building list function | Click drop down arrow next to building. | Building list should appear with county buildings to be selected. | P
7 | Service Desk | Verify list validation for Building list | Manually type Hart Plaza into building list field | Building field display turns red to alert that Hart Plaza is not a valid entry | P
8 | Service Desk | Verify knowledge base article related to summary appears | Type VDI Instructions into summary | VDI instructions knowledge article should appear on the right pane | P |  |  | Tested with "asset"
9 | Service Desk | Service field validation | 1.Click drop down arrow next to service field. 2.Verify services your area (Desktop Support, Enterprise Application etc.)supports is listed under service. 3. Select your team/area of coverage from the list of services, if your team/area of coverage does not exist select enterprise applications. | Incident Services provided by DoIT should appear as an option to be selected under the list of services. Your team/area of coverage should be reflected as the service selected | P
10 | Service Desk | Category, Subcategory, Suggested team validation | Click drop down arrow next to category subcategory field. Verify that the category, subcategory is correctly listed under services that your team/area provides. | The category and subcategory list should appear based on the service that was selected | P
11 | Service Desk | Saving Incident Validation | 1. Without filling the summary and description fields click save | Validation error message appears informing you that the summary and description needs to be filled before incident can be saved. | P
12 | Service Desk/Customer | Saving Incident | 1. Fill out Summary field with TEST your initials and the number one. 2. Click save and note Incident number | Incident Journal show incident# has been logged and email notification will be sent to customer. Incident will change from logged to active. Verify email was sent to the customer. | P
13 | Service Desk/Customer | Changing Status | 1 Open incident you previously just saved. 2.Change status from active to waiting for customer and click save and enter in notes Testing and your initials. Note your incident number. | Incident status changes from active to waiting for customer, a journal entry gets created with your notes and resolution target SLA clock stops, verify email was sent to the customer | P
14 | Service Desk/Customer | Customer Responds to Email | 1. Switch role to self-service user 2. Search for the incident number with status "Waiting for customer" under my items. 3. Pull up incident and enter in note Test 'your initials' response and send note. 4. Next switch role back to service desk analyst and go back to incident. | Email is deplayed in self-service incident and response is displayed in the journal of the incident | P
15 | Service Desk | Creating/Assigning task | 1.Go to Task tab and click New task 2. In Summary enter Test and your Initials. Do the same for details. 3. Select Desktop Support under team and click save | Task will be generated for the Desktop Support , verify email is sent to the team | P
16 | Support Level 2 (Desktop) | Reassigning task | 1. On the task tab click reassign 2. Select the team Enterprise Applications Support. 3. Enter test as the reason for reassignment and click ok. | Task will reassigned from Desktop Support to enterprise applications support | P
17 | Support Level 2 (Desktop) | Completing task/Resolving Incident | 1 Click Accept Task. 2.Click complete under task tab. 3. Select yes when prompt appears to ask if incident can be closed. 4. On actual service select Desktop hardware services, for category select desktop, for subcategory select hard drive, for cause code select hardware. 5. Under resolution detail enter test and your initials, click ok. | Incident Task status will change to completed and the incident status will change to resolved and you should receive an email notification informing you that the incident has been closed | F |  |  | Lydia - check notebook for comments. Revisit task accedpting workflow with Steven.
18 | Support Level 2 (Desktop) | Adding task to resolved ticket validation | 1. Go back to resolved incident 2.Click on task tab. 3. Click new task | Option to click new task is greyed out and new task cannot be created on resolved incident. | F |  |  | Add new task button (on top of screen) is still active on a resolved incident, but it doesn’t let you save. Should gray out button. Revisit all buttons at top of screen. Was able to use assign task to me button but throws an error
19 | Support Level 2 (Desktop) | Closing Incident Validation | 1. Go the incident that you just resolved and validated. 2. Change status to close and save. 3. Add Test 123 to description and resolution field | Error message appears stating that you cannot make any edits to a closed incident | F |  |  | Check notes
21 | Service Desk | Creating Incident using template | 1. Under the service desk analyst role go into the incident module. 2. Click on the dropdown arrow next to new incident. 3. Under the list of templates that appear select WC - Windows Password Reset. 4. Enter in your name under the customer field and select save. | Incident opens with the summary field labeled Windows password reset, the description field displaying "user cannot access windows account". Service- User access services, Category Windows/Network Access, and sub category -password reset. Resolution should display "reset windows password verified that user can log into their account". Actual Service, Category, and Subcategory should display the same information as service, category, and subcategory. Status should be set to resolved. | N/A |  |  | No longer providing templates
Self Service Portal
22 | Customer | Open self-service portal | Go to security role listed under profile and select self-service user | Self-Service Portal Opens to the dashboard
23 | Customer | Verify report an issue link function | Click report an issue link in self service portal | Open self-service incident form
24 | Customer | Customer profile verification | No step needed here | Customer profile should automatically load once you open the self service incident portal
25 | Customer | Incident Notification | 1. Select Building 2. Enter in floor you're currently on. 3. Enter in a alternative phone number, location and asset tag. 4. Enter in a test summary and test description then click save incident. Note: Record the incident number for the next test | A email notification will be sent to your mailbox alerting you that an Incident has been logged for you. You name, location, summary and description should be reflected in the email
26 | Customer | Entering note into self-service incident | 1. Locate the incident ID number from your my items list. 2. Click in the new notes field and type Test and your initials 3. Click save | Note entry appears under activity history
27 | Customer | Adding Attachment | 1.Go back to the incident you previous entered a note into. 2. Under attachment click browse navigate to picture folder and attach a default picture. | Attachment will upload and appear in self service incident
25
26