## Sheet1
Project: Phoenix Ivanti HEAT Upgrade
Knowledge Management Testing
Step | Test Case | Test Execution Steps | Expected Result | Test Result P - Pass F - Failed U - Untested | Date Tested | Tester | Comment
General
1 | Loading Ivanti Site | 1. Open Internet Explorer. 2. Enter https://waynecounty-stg.saasit.com/ in the address bar and press 'Enter'. | Ivanti staging site launches
2 | Log into Ivanti site using your Windows credentials | On Ivanti Site: https://waynecounty-stg.saasit.com enter windows username and password | Successful login to Ivanti SM with Self Service User role
3 | Change user role in Ivanti | If your current role is not "Self Service User" select the drop down arrow next to your current role and select "Self Service User". | Ivanti role changes to "Self Service User"
4 | Opening Knowledge Center Module | Once you are in the "Self Service User Role", click on Knowledge Center on the Ivanti toolbar at the top of the screen. | The Knowledge Center Module will open
Knowledge
5 | Viewing the Search the Knowledge Base Articles search field. | Click on the Knowledge Center Tab "Search the Knowledge Base Articles" search field should be shown. | User is able to view and enter text in the "Search Knowledge Base Articles" field.
6 | Switching Roles | Under your name at the top of the screen select the "Self Service Analyst Role." | Role changed to "Self Service Analyst Role"
7 | Viewing submitted Knowledge Articles | In the Self Service Analyst Role click on More on the top and select Knowledge. | The list of newly created Knowledge documents will be listed.
8 | Filtering Knowledge Articles | On the Knowledge Tab select "Show Filters" Under Author select "Mine" to show any knowledge articles you submitted. | Knowledge articles you submitted will show. If you have not submitted any articles your search will be empty.
9 | Clearing search filter | Deselect "Mine" under Author to clear your current search. | All submitted knowledge base articles will appear.
10 | Opening Knowledge Articles | In the list of knowledge articles double-click to open article number 10592.(How to Use a Desk Phone) | Knowledge article 10592 (How to use a desk phone) will open.
11 | Accessing hyperlinks inside the knowledge article description field. | In the knowledge article 10592 description field scroll down to the bottom of the field and double-click the www.waynecounty.com hyperlink. | The Waynecounty.com website should open in a new IE tab.
12 | Resizing desription field | Using knowledge article 10592, click and drag the light blue 3 dots in the lower right hand corner of the descrtiption field and expand it as far as you can across the screen. | Expanding the description field will readjust text and fields in the affected area.
13 | Saving knowledge article 10592 after reszing description field | Click on "Save" to save the article after you resize the description field. | Knowledge article will not save with the resized description field.
14 | Saving knowledge article 10592 after reszing description field and entering text. | Using knowledge article 10592, with the field expanded, type in "Thank You" after the www.waynecounty.com hyperlink and press "Save" | The knowledge article with save with the description field resized and the text "Thank You"
15 | Emailing knowledge article in "Review" status. | Go back to the list of knowledge articles. Double-click to open knowledge article 10590. Click on the Activity History tab. Under New Record Menu select "New Email". To the far right of the TO field click on the address book icon. The Select Email Addresses window will open, enter your name in the search field and press "GO" . Check the box next to your name and press OK. Enter "Test" in the subject field, enter "test" in the description field and Save your email. | Your email will show as an Outgoing Email. When set up, you will receive an email notifying you to view the knowledge article.
16 | Adding Attachments | Open knowledge article 10590. In the Details tab, go down to the bottom of the screen, next to "Add Searchable Document" click "Upload" to attach another document. Navigate to your saved documents and upload a new attachment. Save the knowledge article. | The original saved attachment will be removed your new attachment will be saved
17 | Adding Attachments in the Attachments Tab | Using the same article 10590 click on the Attachments Tab. Click on New to add additional attachments to the article and press Save. | Additional attachments will be uploaded
18 | Removing/Deleting attachments | Using the same article 10590 on the Attachments Tab click once to highlight your attached files and press Delete. | Selected attachments will be deleted
19 | Viewing Workflow Instances | Using the same article 10590 click on the Workflow Instance tab. Double-click on Approval Workflow - Event Id 3884. The Edit Workflow Instance window will open. Click on "View Instance". The Workflow window will open in another browser. View the workflow steps and close the workflow IE tab when completed.You will be able to view the workflow of document 10590. | You will be able to view the workflow of document 10590.
20 | Viewing Audit History | Using the same article 10590 click on the Audit History tab. Locate the page size option in the lower left hand corner of the screen. Click on the upside down triangle to change the page size to 100. The list of audit history will expand. | Viewing audit history will show operations performed on the knowledge article including the date, user edititing the article, event type, and description.